## How to Use
Medical Assistant — End-to-End Test Plan
Manual E2E test workbook · one command up (./start.ps1) · verify every hop from browser to grounded RAG chat
What this workbook is
Purpose | A step-by-step manual test plan to prove the whole Medical Assistant system works end-to-end: doctor records a consultation → it is transcribed → ingested into a pgvector store → answerable via grounded RAG chat.
How it is organised | 'Scenario Summary' lists every test scenario with its user story and overall expected result. 'Test Steps' is the detailed sheet: one row per step, and for each step exactly how the system should respond (DB row, queue message, blob, status change). 'Environment & Access' and 'Evidence Cheat Sheet' tell you where to look.
How to run a scenario | Work top-to-bottom through the steps of a scenario on the 'Test Steps' sheet. After each action, confirm the 'Expected System Response & Evidence' using the 'Where / How to Verify' column, then record Pass/Fail and any notes.
Before you start (preconditions)
1. Bring the stack up | From the repo root run ./start.ps1 (add -Build to rebuild images). This starts all containers + the frontend and opens the tool tabs. Scenario S01 verifies this.
2. Credentials in .env | Copy compose.env.example to .env. For the full AI path set OPENAI_WHISPER_API_KEY (transcription) and OPENAI_API_KEY (Clinical Knowledge embeddings + chat). Leaving a key blank makes that step fail cleanly — used deliberately in S12/S13.
3. Test login | Doctor: drsmith / Passw0rd!23 (local-dev only). Or register a fresh account in S02.
4. A sample audio file | A short spoken WAV/MP3 (a few seconds, real speech) so the transcript has content the RAG chat can later answer from. Allowed: .wav .mp3 .webm .ogg, ≤100 MB.
Legend
Pass / Fail column | Enter 'Pass' or 'Fail' after verifying each step's evidence.
Failure-path scenario | Rows shaded amber (S12–S13) deliberately break something to prove clean failure handling.
Layer column | Which part of the system the check targets: UI, API, DB (app), DB (ai_med), Queue, Blob, Worker, AI, Telemetry, Ops.
The end-to-end pipeline in one line
Happy path | Browser (5173) → Backend API (7037) → App Postgres + Azurite blob → Outbox relay → RabbitMQ exchange 'medicalassistant.events' → Transcription Worker → OpenAI Whisper (gpt-4o-transcribe) / Azure Speech → Transcript saved → 'transcript-ready.v1' event → Backend consumer → Clinical Knowledge API (8000) → chunk + embed into ai_med pgvector → grounded RAG chat answers with citations.

## Environment & Access
Environment & Access
All values are local-dev only and come from your root .env file.
Component | URL / Endpoint | Port | Auth / Credentials | What to use it for
Frontend (web app) | http://localhost:5173 | 5173 | Log in as doctor (drsmith / Passw0rd!23) | The doctor's UI — the primary test surface.
Backend API | http://localhost:7037 | 7037 | JWT from /api/Auth/login | Auth, patients, consultations, upload, outbox.
Backend API docs (Swagger) | http://localhost:7037/swagger | 7037 | — | Drive/inspect API calls without the UI.
Backend health | http://localhost:7037/health/ready | 7037 | — | Readiness probe (expect 200).
Clinical Knowledge API | http://localhost:8000 | 8000 | Header X-Api-Key: local-development-key | Ingestion + grounded RAG chat (pgvector).
Clinical Knowledge docs | http://localhost:8000/swagger | 8000 | — | Inspect ingestion / chat endpoints.
RabbitMQ management UI | http://localhost:15672 | 15672 | medicalassistant-broker-bootstrap / RABBITMQ_BOOTSTRAP_PASSWORD | Exchange, queues, message + consumer counts.
pgAdmin (DB UI) | http://localhost:5050 | 5050 | Opens in; server pre-registered | Browse both databases and run SQL.
Vector DB UI | http://localhost:8787 | 8787 | postgresql://postgres:postgres@postgres:5432/ai_med | Inspect chunks + embeddings in ai_med.
Aspire Dashboard (telemetry) | http://localhost:18888 | 18888 | — | Traces, metrics and logs from backend + worker.
PostgreSQL (one server, two DBs) | localhost:5432 | 5432 | medicalassistant / POSTGRES_APP_PASSWORD (or postgres/postgres superuser) | MedicalAssistantDb (app) + ai_med (pgvector).
Azurite (Blob emulator) | http://localhost:10000/devstoreaccount1 | 10000 | account devstoreaccount1, well-known dev key | Stored consultation audio/PDF files.
Where the system stores its evidence
Layer | Location / Name | What lives there
App DB — MedicalAssistantDb | Table "AspNetUsers" | Doctor accounts + roles (Identity).
App DB — MedicalAssistantDb | Table "Patients" | Patient demographics, owned by a doctor.
App DB — MedicalAssistantDb | Table "Consultations" | Consultation workflow state, blob refs, failure reason.
App DB — MedicalAssistantDb | Table "Transcripts" | One transcript per consultation (editable text, state).
App DB — MedicalAssistantDb | Table "ConsultationOutboxMessages" | Transactional outbox: EventType, Status, PublishedAtUtc, OccurredAtUtc.
App DB — MedicalAssistantDb | Consultation inbox table | Idempotent consumer rows for transcript-ready; holds ClinicalKnowledge IngestionId/DocumentId/Duplicate result.
AI DB — ai_med (pgvector) | Ingestions | Lifecycle per document: Queued→Processing→Completed/Failed/Superseded/Deleted.
AI DB — ai_med (pgvector) | Chunks | Retrievable units + embeddings (text-embedding-3-large, 3072 dims).
AI DB — ai_med (pgvector) | Quality reports / Patient summaries | One quality report per completed ingestion; rolling per-patient summary.
Message bus | Exchange 'medicalassistant.events' (direct, durable) | Routing keys: consultation.audio-uploaded.v1, .transcript-ready.v1, .transcription-failed.v1, .document-uploaded.v1, .deleted.v1.
Message bus | Transcription Worker queue | Bound only to consultation.audio-uploaded.v1; one live queue plus a .dlq safety net (no automatic-retry queues).
Blob storage | Azurite 'audio' container | Uploaded audio (ref private://consultations/{id}/audio); PDFs similarly.
Telemetry | Aspire Dashboard (18888) | Correlated traces (incl. DB spans), metrics, structured logs.

## Scenario Summary
Scenario Summary
Each scenario expands into detailed, evidence-checked steps on the 'Test Steps' sheet.
ID | Scenario | User Story | Precondition | Overall Expected Result | Type
S01 | Bring up the full stack | As an operator, I want one command to start the whole system so I can confirm it is ready to test. | Docker Desktop running; .env present. | All containers healthy; one-shot jobs Exited(0); health endpoints 200; RabbitMQ exchange + worker queue present; only the seed doctor exists. | Happy path
S02 | Register & log in | As a doctor, I want to register and sign in so I can access my workspace securely. | S01 passed. | Account created in AspNetUsers; login returns a JWT; session persists across refresh. | Happy path
S03 | Create & manage a patient | As a doctor, I want to create, search and edit patients so each encounter has a home. | Logged in (S02). | Patient row created and tied to the doctor; appears in list with stats; edits persist. | Happy path
S04 | Start a consultation (draft) | As a doctor, I want to start a consultation for a patient before recording. | A patient exists (S03). | Consultation row created with Status=Draft; no blob and no event yet. | Happy path
S05 | Audio upload → async transcription (CORE) | As a doctor, I upload a consultation recording and expect an accurate transcript to appear automatically. | A draft consultation exists (S04); transcription key set. | Audio stored in blob; outbox row published; event routed through RabbitMQ; worker transcribes via Whisper/Azure Speech; transcript saved; status reaches Transcribed — every hop leaves the expected evidence. | Happy path
S06 | Transcript auto-ingested into RAG store | As a doctor, I want each transcript to become searchable clinical knowledge without any extra action. | S05 reached Transcribed; OPENAI_API_KEY set on Clinical Knowledge. | transcript-ready event consumed by backend; Clinical Knowledge ingestion Completed; chunks + embeddings written to ai_med with a quality report. | Happy path
S07 | Review & edit a transcript | As a doctor, I want to correct speech-recognition errors before the transcript drives assistance. | S05 produced a transcript. | Transcript displays; edit saves; a new transcript-ready event (higher revision) fires; correction re-ingested (prior chunks superseded). | Happy path
S08 | Grounded RAG chat with citations | As a doctor, I want to ask questions about a patient and get answers grounded in their records with citations. | S06 ingested a transcript for the patient. | Backend routes /api/chat/query to Clinical Knowledge; retrieval is scoped to the patient; a cited, grounded answer is returned. | Happy path
S09 | Insufficient-evidence refusal | As a doctor, I want the assistant to refuse rather than invent an answer when there is no evidence. | A patient with no ingested documents exists. | Chat returns a deterministic insufficient-evidence response; the answer model is not called; nothing is fabricated. | Happy path
S10 | Record now, attach later | As a doctor, I want to capture audio immediately without first choosing a patient. | Logged in. | Draft consultation created with no patient; listed under unassigned recordings; can be attached to a patient afterwards. | Happy path
S11 | Observability / telemetry | As an operator, I want to see an end-to-end trace of a consultation and confirm no sensitive data leaks into logs. | S05 ran at least once. | Aspire shows a single correlated trace across API→outbox→worker→transcript incl. DB spans; logs contain no clinical text or secrets. | Happy path
S12 | Failure: missing transcription key | As an operator, I want a missing transcription credential to fail cleanly, not crash the worker. | Transcription key blanked; worker restarted. | Consultation → Failed with classified code (e.g. speech-key-missing); transcription-failed event on the failure path; no crash, no secret in logs. | Failure path
S13 | Failure: Clinical Knowledge without OpenAI | As an operator, I want ingestion to be recorded and recoverable even if the AI provider is unavailable. | OPENAI_API_KEY blanked on clinical-knowledge; restarted. | POST /ingestions returns 202 + ingestionId but ingestion ends Failed ('No chat provider is configured'); retry after key is set completes it. | Failure path
S14 | PDF / document upload | As a doctor, I want to upload a PDF report and see it handled honestly when no processor is connected. | A consultation exists. | PDF stored; status DocumentUploaded; document-uploaded event published; consultation stays visibly pending with NO placeholder transcript. | Edge case
S15 | Idempotency & duplicate handling | As an operator, I want retries and duplicates not to create double records. | Logged in. | Re-using an Idempotency-Key returns the same consultation; re-ingesting the same document identity yields a duplicate/supersede outcome, not a second document. | Edge case
S16 | Data persists across restart | As an operator, I want a stop/start to preserve data and a volume reset to start clean. | Data created in earlier scenarios. | docker compose stop/start keeps users, patients, consultations, transcripts and chunks; down --volumes wipes and re-migrates from empty. | Ops

## Test Steps
Scenario | Step | User Action / Trigger | Layer | Expected System Response & Evidence | Where / How to Verify | Pass/Fail | Actual Result / Notes
S01 | 1 | Run ./start.ps1 from the repo root. | Ops | All service containers start; one-shot jobs backend-migrations and rabbitmq-provisioner run then exit; tool tabs open in the browser. | docker compose ps — services Up/healthy; migrations & provisioner show 'Exited (0)'.
| 2 | Check backend readiness. | API | Backend reports ready. | curl http://localhost:7037/health/ready → HTTP 200.
| 3 | Check Clinical Knowledge is up. | API | Service serves its OpenAPI doc. | curl http://localhost:8000/swagger/v1/swagger.json → HTTP 200.
| 4 | Open the RabbitMQ management UI. | Queue | Exchange 'medicalassistant.events' exists; the Transcription Worker queue is bound to consultation.audio-uploaded.v1 with consumers = 1. | http://localhost:15672 → Exchanges / Queues tabs.
| 5 | Open pgAdmin. | DB (app) | Server pre-registered; both MedicalAssistantDb and ai_med databases are visible. | http://localhost:5050.
| 6 | Confirm the clean seed. | DB (app) | Only the seed doctor (drsmith) exists; no mock patients or consultations. | pgAdmin: SELECT "UserName" FROM "AspNetUsers"; (one row)
S02 | 1 | Register a doctor in the UI (or confirm drsmith exists). | UI | Registration succeeds; you can proceed to log in. | POST /api/Auth/register → 200/201.
| 2 | Verify the account was stored. | DB (app) | A row exists in AspNetUsers for the username, with the doctor role assigned. | SELECT "UserName" FROM "AspNetUsers";
| 3 | Log in with the credentials. | API | A JWT is returned and the app loads the authenticated dashboard. | POST /api/Auth/login → 200 with token; GET /api/Auth/session → 200.
| 4 | Refresh the browser. | UI | Session persists (JWT held by the frontend); you stay authenticated. | Page stays on an authenticated route; devtools shows stored token.
S03 | 1 | Patients → Add new patient (name + date of birth). | UI | Patient is created and appears in the patient list. | POST /api/Patient → 200/201.
| 2 | Verify persistence. | DB (app) | A Patients row exists, associated with the logged-in doctor's Id. | SELECT * FROM "Patients" ORDER BY "Id" DESC LIMIT 1;
| 3 | Open the patient directory / search. | API | The new patient is listed with consultation statistics. | GET /api/patient returns the patient with stats.
| 4 | Edit the patient and save. | API | The update persists and is reflected on reload. | PUT /api/patient → 200; DB row shows new values.
S04 | 1 | From the patient, start a new consultation. | UI | A draft consultation is created and returns an id. | POST /api/Consultation → 200 with consultation id.
| 2 | Verify initial state. | DB (app) | Consultations row has Status = Draft, no audio blob reference, no failure reason. | SELECT "Id","Status","AudioBlobUri" FROM "Consultations" ORDER BY "Id" DESC LIMIT 1;
| 3 | Confirm nothing has been published yet. | Queue | No integration event has been emitted for this consultation; no outbox row yet. | ConsultationOutboxMessages has no row for this consultation id; RabbitMQ counts unchanged.
S05 | 1 | Upload a short WAV/MP3 to the consultation. | UI | Upload is accepted; the consultation moves to AudioUploaded. | POST /api/Consultation/{id}/audio → 200.
| 2 | Verify the file was stored. | Blob | An audio object exists in the Azurite 'audio' container (reference private://consultations/{id}/audio). | Azurite / storage explorer, or backend logs of the store operation.
| 3 | Check consultation status. | DB (app) | Consultation.Status = AudioUploaded and AudioBlobUri is populated. | SELECT "Status","AudioBlobUri" FROM "Consultations" WHERE "Id"={id};
| 4 | Check the outbox was written in the same transaction. | DB (app) | A ConsultationOutboxMessages row exists: EventType = consultation.audio-uploaded.v1, Status = Pending, PublishedAtUtc = NULL. | SELECT "EventType","Status","PublishedAtUtc" FROM "ConsultationOutboxMessages" ORDER BY "OccurredAtUtc" DESC LIMIT 1;
| 5 | Wait for the outbox relay to publish. | Queue | The outbox row is marked published (PublishedAtUtc set) ONLY after the broker confirms; the message is routed via exchange 'medicalassistant.events'. | Re-run the outbox query (PublishedAtUtc now set); RabbitMQ shows a delivery to the worker queue.
| 6 | Transcription Worker consumes the event. | Worker | A worker inbox row is created (idempotent consumer); consultation status → Transcribing; worker logs show only safe metadata — no audio bytes or transcript text. | Worker container logs; inbox table row; Consultation.Status = Transcribing.
| 7 | Worker calls the transcription provider. | AI | Audio is transcribed within seconds via OpenAI Whisper (gpt-4o-transcribe) or Azure Speech; a provider error would be classified into a failureCode without leaking response bodies. | Worker logs; Aspire trace of the provider call.
| 8 | Transcript is stored. | DB (app) | A Transcripts row (one per consultation) holds the text with completed state. | SELECT "State","ProcessingTimeMs" FROM "Transcripts" WHERE "ConsultationId"={id};
| 9 | Consultation reaches Transcribed. | DB (app) | Consultation.Status = Transcribed. | GET /api/Consultation/{id} → status Transcribed.
| 10 | Worker emits transcript-ready. | Queue | consultation.transcript-ready.v1 is published to the exchange; the payload carries ids/revision only — transcript text is never on the bus. | RabbitMQ: message routed on transcript-ready.v1.
| 11 | Doctor refreshes the consultation page. | UI | The transcript text is visible and stable after refresh; the final status renders correctly (no enum/label mismatch). | Frontend consultation detail page.
S06 | 1 | Backend consumes the transcript-ready event. | DB (app) | The consultation inbox row completes; its ClinicalKnowledge result columns (IngestionId / DocumentId / Duplicate) are populated. | Consultation inbox table row for transcript-ready shows the ingestion result.
| 2 | Backend calls Clinical Knowledge to ingest. | AI | POST /ingestions is accepted (202 + ingestionId) for a SessionTranscript document. | GET /ingestions/{id} with header X-Api-Key: local-development-key.
| 3 | Ingestion completes. | DB (ai_med) | The Ingestions row moves Queued → Processing → Completed. | GET /ingestions/{id} → status Completed; or query ai_med Ingestions.
| 4 | Chunks + embeddings are written. | DB (ai_med) | Chunk rows are created with embeddings (text-embedding-3-large, 3072 dims); a quality report row exists for the ingestion. | Vector DB UI (8787) or GET /ingestions/{id}/quality.
| 5 | Patient documents reflect the new content. | AI | The transcript now appears among the patient's current documents. | GET /patients/{patientId}/documents.
S07 | 1 | Open the consultation and view the transcript. | API | The transcript text is returned and displayed. | GET /api/transcript/{consultationId} → 200.
| 2 | Edit the transcript text and save. | API | The corrected text is saved. | PUT /api/transcript/{consultationId} → 200; DB text updated.
| 3 | Confirm the correction is re-announced. | Queue | A new consultation.transcript-ready.v1 is published with an incremented revision. | RabbitMQ: transcript-ready.v1 with higher revision.
| 4 | Confirm downstream correction semantics. | DB (ai_med) | Re-ingesting the same document identity supersedes the prior chunks (the earlier ingestion becomes Superseded). | ai_med Ingestions: prior row status Superseded; new row Completed.
S08 | 1 | Open the patient chat and ask a question answerable from the transcript (e.g. 'What symptoms were discussed?'). | UI | A grounded answer is returned with citations. | POST /api/chat/query → 200 with answer + citations.
| 2 | Confirm the backend routes to the real RAG service. | AI | The backend calls the Clinical Knowledge grounded-answer endpoint (not a legacy AI URL). | Aspire trace / Clinical Knowledge logs show /patients/{patientId}/chat/answer.
| 3 | Confirm retrieval is patient-scoped. | AI | The query is embedded and pgvector search is scoped to this patient; evidence clears the threshold. | Clinical Knowledge logs / trace.
| 4 | Verify the answer is grounded. | UI | The answer cites evidence labels that map back to source chunks and is consistent with the transcript (not hallucinated). | Read the answer + citations against the transcript.
S09 | 1 | Ask a chat question about a patient with no ingested documents. | UI | A deterministic insufficient-evidence response is returned; nothing is fabricated. | POST /api/chat/query → refusal response.
| 2 | Confirm the model was not invoked needlessly. | AI | Because evidence is below threshold, the answer-generation model is not called. | Clinical Knowledge logs show refusal before generation.
S10 | 1 | Open Record without selecting a patient; record and stop. | UI | A draft consultation is created without a patient and the audio is uploaded. | POST /api/Consultation + /audio succeed.
| 2 | Confirm it is unassigned. | DB (app) | The consultation has no patient id and appears under unassigned recordings. | GET /api/consultation/drafts/unattached lists it.
| 3 | Attach it to a patient. | API | The consultation is now linked to the chosen patient. | PUT /api/consultation/{id}/patient → 200.
| 4 | Note the known caveat. | AI | Attaching updates the consultation but does not currently republish it for downstream AI ingestion. | Expected behaviour — record as a known limitation, not a failure.
S11 | 1 | Open the Aspire Dashboard. | Telemetry | Traces, metrics and logs from the backend and worker are visible. | http://localhost:18888.
| 2 | Trace one consultation's flow. | Telemetry | A single correlated trace spans API → outbox → worker → transcript, including DB spans. | Aspire Traces, filtered by the correlation id.
| 3 | Inspect the logs for leaks. | Telemetry | No transcript text, audio, secrets or provider response bodies appear in any log line. | Aspire structured logs.
S12 | 1 | Blank OPENAI_WHISPER_API_KEY (or the Azure Speech key), restart the worker, then upload audio. | Ops | The worker classifies the failure (e.g. speech-key-missing) and does not crash. | Worker logs show the classified code; no stack trace of the secret.
| 2 | Check the consultation outcome. | DB (app) | Consultation.Status = Failed with a user-safe FailureReason. | SELECT "Status","FailureReason" FROM "Consultations" WHERE "Id"={id};
| 3 | Check the failure event. | Queue | consultation.transcription-failed.v1 is emitted on the failure path (routed to the bounded audit queue; no infinite retry). | RabbitMQ: transcription-failed handling; audit queue receives it.
| 4 | Confirm there is NO automatic retry. | Queue | The worker queue has no .retry.* queues; the message is acknowledged (not re-queued) after the failure is recorded. Only a .dlq safety net exists. | RabbitMQ Queues: only the main queue + .dlq; message count returns to 0.
| 5 | Restore the key, then retry from the UI. | UI | Clicking Retry on the failed consultation re-runs transcription from the stored audio; status returns to AudioUploaded then Transcribed. | POST /api/consultation/{id}/retry; watch status progress.
S13 | 1 | Blank OPENAI_API_KEY on clinical-knowledge, restart it, then trigger an ingestion. | Ops | The API still accepts the request. | POST /ingestions → 202 with an ingestionId.
| 2 | Check the ingestion outcome. | DB (ai_med) | The ingestion ends Failed with a clear reason ('No chat provider is configured'). | GET /ingestions/{id} → status Failed.
| 3 | Confirm the indexing failure is surfaced (no auto-retry). | DB (app) | The transcript-ready consumer records the failure and sets the consultation FailureReason (status stays Transcribed, transcript still viewable); the message is acknowledged, not re-queued. | GET /api/Consultation/{id} shows failureReason; no .retry.* queues in RabbitMQ.
| 4 | Recover via manual retry. | UI | After restoring the key, the doctor clicks Retry on the consultation; the backend re-publishes transcript-ready and ingestion completes. | POST /api/consultation/{id}/retry → ai_med ingestion Completed; failureReason clears.
S14 | 1 | Upload a PDF to a consultation. | UI | The PDF is stored and the consultation moves to DocumentUploaded. | POST /api/Consultation/{id}/document → 200; blob stored.
| 2 | Check the event. | Queue | consultation.document-uploaded.v1 is published to the exchange. | ConsultationOutboxMessages / RabbitMQ show the document event.
| 3 | Confirm honest pending state. | DB (app) | No Document Processor is bound, so the consultation stays visibly pending with NO placeholder transcript created. | No Transcripts row is fabricated; status remains pending document processing.
S15 | 1 | Create a consultation twice with the same Idempotency-Key header. | API | The second call returns the same consultation; no duplicate row is created. | POST /api/Consultation with header Idempotency-Key; one DB row.
| 2 | Re-ingest the same document identity. | AI | The service returns a duplicate/conflict outcome or supersedes, rather than creating a second document. | POST /ingestions with same identity → duplicate/superseded outcome.
S16 | 1 | Run docker compose stop, then docker compose start (or ./stop.ps1 then ./start.ps1). | Ops | All data is preserved: users, patients, consultations, transcripts and ai_med chunks are unchanged. | Compare row counts in pgAdmin before and after.
| 2 | Run docker compose down --volumes (./stop.ps1 -Reset). | Ops | Volumes are wiped and the app re-migrates from empty on next start (only the seed doctor remains). | After restart: AspNetUsers has just drsmith; no patients/consultations.

## Evidence Cheat Sheet
Evidence Cheat Sheet
Copy-paste checks to verify each hop. Replace {id}. Postgres identifiers are quoted (PascalCase).
Check | Command / Query | Expected
Container status | docker compose ps | All Up/healthy; backend-migrations & rabbitmq-provisioner = Exited (0).
Backend health | curl -s -o NUL -w "%{http_code}" http://localhost:7037/health/ready | 200
Clinical Knowledge health | curl -s -o NUL -w "%{http_code}" http://localhost:8000/swagger/v1/swagger.json | 200
Seed doctor only | psql MedicalAssistantDb -c 'SELECT "UserName" FROM "AspNetUsers";' | One row: drsmith.
Consultation status | psql -c 'SELECT "Id","Status","AudioBlobUri" FROM "Consultations" ORDER BY "Id" DESC LIMIT 5;' | Draft → AudioUploaded → Transcribing → Transcribed.
Outbox published? | psql -c 'SELECT "EventType","Status","PublishedAtUtc" IS NOT NULL AS published FROM "ConsultationOutboxMessages" ORDER BY "OccurredAtUtc" DESC LIMIT 5;' | audio-uploaded.v1 row; published = true after relay runs.
Transcript exists | psql -c 'SELECT "ConsultationId","State" FROM "Transcripts" ORDER BY "Id" DESC LIMIT 5;' | One row per consultation; State completed.
RabbitMQ queues | Open http://localhost:15672 → Queues | Worker queue bound to audio-uploaded.v1; consumers = 1; messages flow through.
Ingestion status | curl -s http://localhost:8000/ingestions/{id} -H "X-Api-Key: local-development-key" | status: Completed (or Failed on the S13 drill).
Chunks written | Vector DB UI (8787): SELECT count(*) FROM chunks; (ai_med) | Non-zero after S06; embeddings present (3072 dims).
Grounded chat | POST /api/chat/query with a patient question (via UI or Swagger) | Answer + citations, or deterministic refusal when no evidence.
Telemetry | Open http://localhost:18888 | Correlated traces incl. DB spans; no clinical text/secrets in logs.