## Overview
Full-System E2E Alignment - Task List
Aligns the medical-assistant frontend, backend API, application PostgreSQL database, Blob Storage/Azurite, RabbitMQ event bus, standalone Transcription Worker with real Azure Speech, Clinical Knowledge API, and clinical PostgreSQL database so a real doctor-style user can run the complete consultation journey end to end. Work rule: implement one task at a time, keep tasks reviewable, and only mark Completed after the relevant local evidence is captured.
The two invariants every E2E alignment task must preserve
1. The real user journey is the truth: browser-visible behavior, backend state, event delivery, transcription, and Clinical Knowledge ingestion must agree.
2. Clinical content stays protected: no transcript/audio content, filenames, Blob URIs, secrets, provider bodies, or raw payloads are copied into logs, broker evidence, screenshots, or task notes.
Primary references: project-docs/event bus implementations/14-clean-environment-release-gate.md, docker-compose.yml, compose.env.example, frontend/.env.example, backend and AI appsettings.
Phase | Total Tasks | Completed | Remaining
0 - Runtime Contract | 4 | 1 | 3
1 - Databases & Storage | 5 | 0 | 5
2 - API & Frontend Alignment | 5 | 0 | 5
3 - Event Pipeline & Azure Speech | 6 | 0 | 6
4 - Real User Journey | 6 | 0 | 6
5 - E2E Automation & Evidence | 5 | 0 | 5
6 - Clean Release Rehearsal | 3 | 0 | 3
Total | 34 | 1 | 33

## Tasks
ID | Phase | Title | The Task | How it contributes to the bigger picture | Depends On | Status | Notes
E01 | 0 - Runtime Contract | Confirm real-user product journey | Write the canonical local E2E journey: doctor registers/logs in, creates or selects a patient, uploads audio, waits for transcription, reviews transcript, and verifies Clinical Knowledge ingestion/search. Define expected visible status transitions and what evidence proves each hop. | Keeps every technical alignment tied to the product promise: a real clinician can turn a consultation recording into usable clinical text and knowledge. |  | Completed | Implemented: canonical real-user E2E journey documented in project-docs/e2e-alignment/01-real-user-e2e-journey.md, including visible status progression and safe evidence per browser/backend/storage/event/worker/Speech/Clinical Knowledge hop.
E02 | 0 - Runtime Contract | Create local runtime environment file | Create a local ignored environment file from compose.env.example. Add the real Azure Speech key and region supplied by the user, confirm all local passwords/API keys are consistent across Compose, backend, worker, and Clinical Knowledge. | One source of truth prevents the classic local E2E gremlin: each service running with a different secret or endpoint. | E01 | Not Started
E03 | 0 - Runtime Contract | Clean confusing legacy/runtime leftovers | Archive or remove untracked obsolete Function/transcriber workspace leftovers and stale scratch artifacts that can confuse startup checks. Keep only intentional helper files or document why they remain. | The local workspace should visually match the no-Azure-Functions architecture before real E2E testing begins. | E01 | Not Started
E04 | 0 - Runtime Contract | Define run modes and ports | Document the supported local run mode: Compose for backend dependencies/services, Vite for frontend, HTTP backend base URL, exposed ports, health endpoints, and RabbitMQ management UI. Decide whether frontend runs outside Compose for the first E2E pass. | Makes the project startable by a human without guessing which of several old launch profiles is authoritative. | E01 | Not Started
E05 | 1 - Databases & Storage | Clean Compose infrastructure start | From empty volumes, start postgres-app, postgres-clinical, rabbitmq, rabbitmq-provisioner, azurite, backend-migrations, backend-api, transcription-worker, and clinical-knowledge. Capture first startup failures without masking them. | Proves the whole system can stand up from nothing rather than from accidental local state. | E02, E04 | Not Started
E06 | 1 - Databases & Storage | App database migration and identity seed | Verify backend-migrations creates the application schema, the API does not apply migrations on startup, identity roles seed successfully, and register/login works against the clean app DB. | A real user cannot begin the product journey unless auth and core schema initialize cleanly. | E05 | Not Started
E07 | 1 - Databases & Storage | Clinical Knowledge database initialization | Inspect and run the Clinical Knowledge schema path against postgres-clinical. If startup does not initialize schema, add the missing migration/bootstrap step or documented command. | The final transcript handoff depends on the AI module having a valid pgvector-backed database, not just a listening HTTP port. | E05 | Not Started
E08 | 1 - Databases & Storage | Blob container bootstrap and access | Verify Azurite containers for audio and PDF exist or are created by the app. Upload and read a tiny synthetic object through the same backend/worker connection settings. | Audio upload and transcription are connected through Blob Storage; a broken container name strands the user journey before Speech starts. | E05 | Not Started
E09 | 1 - Databases & Storage | Database schema smoke queries | Add or run a small smoke check that verifies required app tables, Clinical Knowledge tables/extensions, outbox/inbox tables, and migration history after clean startup. | Turns database alignment into quick evidence instead of discovering missing tables mid-demo. | E06, E07 | Not Started
E10 | 2 - API & Frontend Alignment | Backend health, Swagger, and auth smoke | Verify /health/live, /health/ready, Swagger, register, login, and authenticated session/profile endpoints work through http://localhost:7037. | Confirms the backend is usable from the same public edge the browser will call. | E06 | Not Started
E11 | 2 - API & Frontend Alignment | Frontend API base URL alignment | Change local frontend configuration from https://localhost:7037/api to http://localhost:7037/api for Compose-backed backend testing, or configure backend HTTPS consistently if that path is chosen. | Without this, a real browser test fails before it reaches product logic. | E04, E10 | Not Started
E12 | 2 - API & Frontend Alignment | Backend CORS alignment for Vite | Ensure backend CORS allows the actual Vite origin, usually http://localhost:5173, while keeping credentials/auth behavior intact. | Lets the real frontend call the real backend rather than relying on API tools only. | E10, E11 | Not Started
E13 | 2 - API & Frontend Alignment | Frontend build and route smoke | Run npm install/build/lint as appropriate, start Vite, open login/dashboard/patient/consultation routes, and fix type/API mismatches that block the user journey. | The browser is the user’s instrument panel; it must align with current backend contracts. | E11, E12 | Not Started
E14 | 2 - API & Frontend Alignment | Consultation and patient API contract check | Exercise create patient, list patients, create consultation, assign patient, upload audio, get consultation details, get transcript, and delete consultation endpoints. Compare responses with frontend TypeScript types. | Prevents subtle UI failures after successful backend work, especially around status names and IDs. | E10, E13 | Not Started
E15 | 3 - Event Pipeline & Azure Speech | RabbitMQ topology verification | Verify exchange, backend subscriber queue, transcription-worker queue, retry queues, DLQs, bindings, and least-privilege users exist after clean startup. | The broker must route facts to the right capability before a user upload can complete asynchronously. | E05 | Not Started
E16 | 3 - Event Pipeline & Azure Speech | Outbox relay live publish proof | Upload or seed an audio consultation and verify the backend writes an outbox row, claims it, publishes with confirm, and marks it published without request-thread direct publishing. | This is the bridge between accepted upload and asynchronous processing. | E08, E14, E15 | Not Started
E17 | 3 - Event Pipeline & Azure Speech | Transcription Worker readiness and consumption | Confirm the worker connects to RabbitMQ, binds only audio-uploaded events, consumes the uploaded event, writes inbox state, and transitions the consultation into processing. | Proves the Azure Function replacement is alive in the real stack, not just in unit tests. | E15, E16 | Not Started
E18 | 3 - Event Pipeline & Azure Speech | Azure Speech credential and sample audio proof | With real Azure Speech key/region, run a short known-good audio sample through the worker and verify provider success or actionable provider error classification. | Real transcription is the heart of the product; this separates cloud credential/audio-format issues from local plumbing issues. | E02, E17 | Not Started
E19 | 3 - Event Pipeline & Azure Speech | Transcript Ready handoff to backend | Verify successful transcription writes Transcript, publishes consultation.transcript-ready.v1, and the backend subscriber consumes it idempotently. | Moves from raw transcription to the backend-owned clinical knowledge boundary. | E18 | Not Started
E20 | 3 - Event Pipeline & Azure Speech | Clinical Knowledge ingestion handoff | Verify backend submits the completed transcript to Clinical Knowledge using the configured API key/base URL and records ingestion/document identity without duplicating on retry. | This completes the product value loop: a consultation becomes searchable clinical knowledge. | E07, E19 | Not Started
E21 | 4 - Real User Journey | Register and login as doctor | Through the frontend, register a new doctor account, login, persist JWT/session state, refresh the browser, and confirm authenticated routes remain usable. | Validates the first real user touchpoint, not just backend auth endpoints. | E12, E13 | Not Started
E22 | 4 - Real User Journey | Create patient from UI | Create a patient through the UI, verify dashboard/patient lists update, and confirm the database stores the patient for the authenticated doctor. | Gives the consultation a realistic owner/context for doctor workflows. | E21 | Not Started
E23 | 4 - Real User Journey | Upload real audio consultation from UI | Upload a short Azure Speech-compatible audio file through the patient or new-consultation UI. Verify progress, backend upload response, Blob object creation, and AudioUploaded status. | This is the visible start of the core product workflow. | E18, E22 | Not Started
E24 | 4 - Real User Journey | Observe status progression to transcript | From the browser, poll/watch the consultation detail page move through processing states until transcript text is visible. Verify no stale status or frontend enum mismatch blocks display. | Lets the user experience the asynchronous system as a coherent product instead of separate services. | E19, E23 | Not Started
E25 | 4 - Real User Journey | Verify Clinical Knowledge result is usable | Use the available UI/API path to confirm the ingested consultation is retrievable/searchable or at least durably accepted by Clinical Knowledge with recorded document identity. | Proves the transcript creates downstream value beyond being stored text. | E20, E24 | Not Started
E26 | 4 - Real User Journey | Correction and deletion smoke | Edit/correct transcript if UI/API supports it, verify a new Transcript Ready handoff, then delete the consultation and confirm Blob/Clinical Knowledge cleanup converges without resurrecting content. | Checks the clinically important lifecycle edges after the happy path works. | E25 | Not Started
E27 | 5 - E2E Automation & Evidence | Local E2E runbook | Create a concise runbook with prerequisites, secrets, startup, health checks, real-user path, RabbitMQ/DB inspection commands, Azure Speech troubleshooting, and shutdown/cleanup. | Gives us and future reviewers the exact ritual for reproducing the full product path. | E05, E20 | Not Started
E28 | 5 - E2E Automation & Evidence | API smoke script | Create a safe local script or documented command sequence for register/login, patient creation, consultation creation, audio upload, status polling, transcript retrieval, and evidence capture. | Provides fast repeatable checks before opening the browser. | E14, E20 | Not Started
E29 | 5 - E2E Automation & Evidence | Browser E2E test skeleton | Add Playwright or equivalent browser E2E skeleton only after manual UI flow is stable. Cover login, patient creation, audio upload, polling, and transcript visibility. | Turns the real-user path into regression coverage once the seams stop moving. | E24, E28 | Not Started
E30 | 5 - E2E Automation & Evidence | Operational evidence pack | Define where to record container status, health checks, RabbitMQ queue state, DB rows, outbox/inbox records, worker logs, and Clinical Knowledge ingestion ID for each E2E run. | Makes failures diagnosable without copying clinical content into notes or logs. | E20, E27 | Not Started
E31 | 5 - E2E Automation & Evidence | Failure-mode mini checks | Run at least broker unavailable at upload, worker stopped before consumption, and bad Speech credential/sample classifications after the happy path is stable. | Confirms the system is robust enough for real use, not just a fair-weather demo. | E24, E30 | Not Started
E32 | 6 - Clean Release Rehearsal | Clean volumes full rehearsal | Run the complete documented startup and happy-path E2E from docker compose down --volumes through final transcript/Clinical Knowledge evidence. | This is the final proof that no hidden local state is required. | E27, E28, E31 | Not Started
E33 | 6 - Clean Release Rehearsal | Backup and restore rehearsal | In a disposable environment, create representative state, back up app/clinical DBs and RabbitMQ definitions, destroy volumes, restore, and verify outbox/inbox/transcript/Clinical Knowledge/deletion state reconcile. | Protects the project as an operable product capability rather than a one-time local success. | E32 | Not Started
E34 | 6 - Clean Release Rehearsal | Final user acceptance signoff | Run the manual browser journey with real Azure Speech credentials, collect evidence, list known limitations, and mark the system ready for broader review or deployment prep. | This is the point where the project becomes ready for you to test like a real user with confidence. | E33 | Not Started

## Implementation Plan
Full-System E2E Alignment Groups & Review Gates
Groups reduce context switching but do not combine review gates. A task is done only when the matching code/config/doc change has been reviewed and its local evidence is captured. Prefer finishing the first unblocked task before starting later tasks unless a dependency investigation is read-only.
Review workflow | 1. Inspect current seam | 2. Implement one task | 3. Run focused check | 4. Capture evidence | 5. Review code | 6. Commit/complete | No batch approval
Group | Workstream | Tasks | Safe parallel work | Review sequence | Start gate | Group exit gate
G00 | Runtime contract | E01-E04 | E02 and E03 can proceed after E01; E04 can proceed with E02 | E01 → E02/E03/E04 | Repo docs and current Compose inspected | One authoritative local run contract
G01 | Clean infrastructure and schemas | E05-E09 | E06/E07/E08 can be investigated after E05 | E05 → E06/E07/E08 → E09 | Runtime contract complete | Both databases/storage initialize from clean state
G02 | Browser/API alignment | E10-E14 | E11/E12 can pair; E13 follows; E14 checks contracts | E10 → E11/E12 → E13 → E14 | Backend reachable | Frontend can call current backend APIs
G03 | Event and Azure Speech pipeline | E15-E20 | E15/E16/E17 build the pipeline; E18 requires real keys; E19/E20 follow success | E15 → E16 → E17 → E18 → E19 → E20 | Databases/storage/API aligned | Upload reaches transcription and Clinical Knowledge
G04 | Manual real-user journey | E21-E26 | Sequential because each step validates the next user-visible state | E21 → E22 → E23 → E24 → E25 → E26 | Pipeline works at service/API level | Doctor can complete the product journey in browser
G05 | Automation and evidence | E27-E31 | E27/E28/E30 can start after service journey; E29 after manual UI stability | E27 → E28/E30 → E29/E31 | Manual journey understood | Repeatable E2E checks and evidence capture
G06 | Release rehearsal | E32-E34 | Sequential final gates | E32 → E33 → E34 | Automation/evidence ready | Clean-environment E2E signoff

## E2E User Journey
Step | User action / system event | Primary surface | Expected evidence | Related tasks
1 | Doctor registers and logs in | Frontend + backend auth | JWT/session works; roles seeded in app DB | E06, E10, E21
2 | Doctor creates/selects patient | Frontend patient pages | Patient is visible in UI and belongs to authenticated doctor | E14, E22
3 | Doctor uploads audio consultation | Frontend upload + backend API | Blob stored; Consultation status becomes AudioUploaded; outbox row exists | E08, E16, E23
4 | Outbox relay publishes Audio Uploaded | Backend background service + RabbitMQ | Published outbox row; event reaches worker queue | E15, E16
5 | Worker transcribes with Azure Speech | Transcription Worker | Inbox state, Speech success, Transcript stored | E17, E18, E19
6 | Backend receives Transcript Ready | Backend subscriber | Backend inbox completed; Clinical Knowledge request sent | E19, E20
7 | Clinical Knowledge ingests transcript | Clinical Knowledge API + DB | Ingestion/document identity recorded; duplicate retry is safe | E20, E25
8 | Doctor sees result | Frontend consultation detail | Final status/transcript visible; no browser/API mismatch | E24, E25
9 | Doctor corrects or deletes consultation | Frontend/API lifecycle actions | Correction republishes; deletion cleanup converges | E26