## Overview & Decisions
Doctor ↔ AI Conversations — Implementation Plan
Medical Assistant · grounded RAG chat with history, live progress, and interactive citations · v1
Goal
Add persistent doctor↔AI conversations to the existing patient-scoped RAG chat: durable history per doctor+patient, real-time “what the system is doing” progress over SignalR (the answer itself is NOT streamed), structured & interactive citations, and a rolling-summary context window. The AI service stays stateless (ADR-0010); all conversation state lives in the backend MedicalAssistantDb.
# | Decision area | Decision (locked) | Rationale
D1 | State ownership | Conversation history in backend MedicalAssistantDb; AI service stays stateless. | Honors ADR-0010 (AI stores nothing); backend already passes RecentTurns/PriorSummary into the AI.
D2 | Progress fidelity | Real phase transitions (not scripted on a timer). | Honest and debuggable; each message fires when a real step actually starts.
D3 | Progress transport | One NEW backend SignalR hub /hubs/chat (client method 'ChatProgress', routed by doctorId) — the only hub the browser touches. | Consistent with the existing ingestion hub pattern; per-doctor routing for many doctors.
D4 | AI→backend hop | AI reports phases via X-Api-Key HTTP callback POST /api/ai-callback/chat-progress. | Reuses the existing AiCallbackController pattern; no persistent hub-client in the backend.
D5 | Answer delivery | Answer returns WHOLE as the POST /api/chat/ask HTTP 200 body — never token-streamed. | Explicit requirement; hub carries status only, HTTP carries the answer.
D6 | Conversation scope | One doctor + one patient (optional consultation tag). | Patient is already the hard retrieval boundary (ADR-0011); clean history browse per patient.
D7 | History context | Last 6 messages replayed verbatim + a rolling LLM summary for older history. | Follow-ups keep their referent; summary is phrasing/refinement input only, never evidence.
D8 | Summary refresh | Async in backend (off the answer's critical path) via new AI /chat/summarize; window-aligned: skip under 6 msgs, then refresh every 6 new msgs. | Zero added answer latency; cadence=window means no gap/overlap; ~6× fewer summarize calls than per-turn.
D9 | Citations | Backend stops flattening to strings; passes STRUCTURED citations through and persists them. | Required for durable, richly-rendered citations; current code loses ChunkId/DocumentId/Score/date.
D10 | Citation UX | Parse verified inline [E#] markers into anchors: hover → quote popover; click → expand citation card. No source deep-link in v1. | Transcripts are single-line prose, so line-range deep-linking is unreliable; the verbatim Quote is the reliable anchor.
D11 | Conversation lifecycle | Explicit 'New conversation' button PLUS auto-create + auto-title on first question; rename / soft-delete allowed. | Low friction (just start asking) while still allowing deliberate new threads.
D12 | Turn failure | Persist user msg immediately; assistant state Pending→Completed/Refused/Failed. Failures save with reason + inline Retry (idempotent on askId). No auto-retry. | Matches the doctor-triggered manual-retry pattern already used for transcription/ingestion. A refusal is a normal answer, not a failure.
D13 | Ask endpoint shape | Unified POST /api/chat/ask { patientId, conversationId?, question, askId }; auto-creates when conversationId is absent. | Single 'send a question' code path for first and Nth question; explicit New just creates first, then passes the id.

## Implementation Plan
Implementation Plan — phased & sequenced
Status legend: Not started · In progress · Done · Blocked. Depends On references Task IDs.
Phase | ID | Layer | Task | Details | Location / files | Depends on | Acceptance criteria | Status
P0 Data model | P0.1 | Backend/Domain | Add Conversation, ChatMessage, MessageCitation entities | Conversation(DoctorId, PatientId, ConsultationId?, Title, RollingSummary?, SummarizedThroughSeq?, Status, timestamps). ChatMessage(ConversationId, Sequence, Role, Content, State, FailureReason?, Language?, AskId, CreatedAtUtc). MessageCitation(Label, ChunkId, DocumentId, DocumentType, SessionId?, DocumentDate?, SourceRef?, Quote, Score). | backend/src/MedicalAssistant.Domain | — | Entities compile; navigation props wired (Conversation 1..* ChatMessage 1..* MessageCitation). | Not started
P0 Data model | P0.2 | Backend/Domain | Add enums MessageRole, MessageState, ConversationStatus | MessageRole {User, Assistant}. MessageState {Pending, Completed, Refused, Failed}. ConversationStatus {Active, Archived}. | backend/src/MedicalAssistant.Domain/Enums | P0.1 | Enums referenced by entities; stored as int or string per existing convention. | Not started
P0 Data model | P0.3 | Backend/Persistence | EF Core configurations + DbSets | IEntityTypeConfiguration for each table: keys, FKs, indexes (ConversationId+Sequence unique; DoctorId+PatientId; AskId). Add DbSets to the app DbContext. | backend/src/MedicalAssistant.Persistence/Configurations | P0.1,P0.2 | Model builds; indexes present; cascade delete Conversation→Messages→Citations. | Not started
P0 Data model | P0.4 | Backend/Migrations | EF migration 'AddChatConversations' | Generate + review migration; apply against MedicalAssistantDb. Follow existing migration project layout. | backend/src/MedicalAssistant.Migrations | P0.3 | Migration applies cleanly up & down on a fresh DB; three tables created. | Not started
P1 Citations passthrough | P1.1 | Backend/Application | Structured citation contract (stop flattening) | Replace List<string> Citations with a structured ChatCitationDto (Label, ChunkId, DocumentId, DocumentType, SessionId?, DocumentDate?, SourceRef?, Quote, Score). Update ChatResponseDto. | backend/src/MedicalAssistant.Application/Features/Chat | — | ChatResponseDto exposes structured citations; old string list removed or mapped for back-compat. | Not started
P1 Citations passthrough | P1.2 | Backend/Infrastructure | Map AI ChatCitation → ChatCitationDto | Update ClinicalKnowledgeHttpClient to deserialize the full citation objects (not just Quote) and map to the structured DTO. | backend/src/MedicalAssistant.Infrastructure/ClinicalKnowledge/ClinicalKnowledgeHttpClient.cs | P1.1 | All AI citation fields survive the hop; verified by a mapping unit test. | Not started
P2 Backend orchestration | P2.1 | Backend/Persistence | Conversation & message repositories | IConversationRepository: Create, GetForDoctor, ListByPatient, AddMessage, GetMessages(+citations), UpdateSummary, Rename, SoftDelete. Ownership checks (doctorId). | backend/src/MedicalAssistant.Persistence/Repositories | P0.4 | Repo methods enforce doctor ownership; messages returned ordered by Sequence with citations. | Not started
P2 Backend orchestration | P2.2 | Backend/Application | AskChat command handler (the core turn) | POST /api/chat/ask: resolve patient (reuse existing logic); auto-create+title conversation if conversationId null; persist User msg; persist Assistant msg Pending; build context (P3.3); call AI; on success persist answer+citations, state=Completed (or Refused); on error state=Failed+reason. Return persisted assistant message. | backend/src/MedicalAssistant.Application/Features/Chat/.../AskChat | P1.2,P2.1,P4.3 | New & existing-conversation asks both persist correctly; refusal saved as Refused; response carries conversationId+structured citations. | Not started
P2 Backend orchestration | P2.3 | Backend/Application | askId idempotency | If a message with the same AskId already exists in a terminal state, return it instead of re-asking. Guards double-submit and powers retry. | backend/src/MedicalAssistant.Application/Features/Chat | P2.2 | Re-posting the same askId returns the original result; no duplicate assistant message. | Not started
P2 Backend orchestration | P2.4 | Backend/API | Conversation CRUD endpoints | POST /api/conversations (explicit new); GET /api/patients/{patientId}/conversations (history list); GET /api/conversations/{id}/messages (+citations); PATCH /api/conversations/{id} (rename); DELETE /api/conversations/{id} (soft). | backend/src/MedicalAssistant.Api/Controllers/ChatController.cs (+Conversations) | P2.1 | All endpoints authorized to the owning doctor; list/detail reopen full history with structured citations. | Not started
P2 Backend orchestration | P2.5 | Backend/API | Retry endpoint | POST /api/conversations/{id}/messages/{messageId}/retry: re-run a Failed turn reusing its askId (idempotent). Transitions Failed→Pending→Completed/Refused/Failed. | backend/src/MedicalAssistant.Api/Controllers | P2.2,P2.3 | Retrying a Failed turn produces a Completed/Refused turn in place; success is idempotent. | Not started
P2 Backend orchestration | P2.6 | Backend/Application | Auto-title generation | Derive title from first question (trim ~60 chars) OR a cheap model-made title. Applied at auto-create and on explicit-create-then-first-ask. | backend/src/MedicalAssistant.Application/Features/Chat | P2.2 | New conversation gets a sensible, non-empty title; renamable via PATCH. | Not started
P3 Rolling summary | P3.1 | AI service | New POST /patients/{id}/chat/summarize | Input { priorSummary, newTurns }; output { updatedSummary }. Stateless; reuses the model provider. Bounded output length. | AI/src/MedicalAssistance.Ingestion.Api/Controllers + Chat | — | Endpoint returns a coherent merged summary; deterministic contract documented. | Not started
P3 Rolling summary | P3.2 | Backend/Application | Async window-aligned summary refresh | After returning the answer, background-trigger a refresh only when messagesSinceLastSummary >= 6 and total messages > 6. Call AI /chat/summarize, store RollingSummary + SummarizedThroughSeq. | backend/src/MedicalAssistant.Application/Features/Chat | P2.2,P3.1 | No summary under 6 msgs; refresh fires once per 6 new msgs; answer latency unchanged. | Not started
P3 Rolling summary | P3.3 | Backend/Application | Context builder (last 6 verbatim + summary) | Assemble RecentTurns (last 6 messages) + PriorSummary (RollingSummary) and pass into the AI ask request. | backend/src/MedicalAssistant.Application/Features/Chat | P2.1 | AI request carries exactly the last 6 turns + current summary; unit-tested boundary behaviour. | Not started
P4 Progress transport | P4.1 | Backend/API | ChatHub + per-doctor routing | Add ChatHub : Hub (empty, one-way). AddSignalR + MapHub('/hubs/chat'). IUserIdProvider maps JWT→doctorId so Clients.User(doctorId) routes correctly. JWT auth via accessTokenFactory. | backend/src/MedicalAssistant.Api (Realtime/ChatHub.cs, Program.cs) | — | Authenticated browser connects; server can push to a single doctor's clients. | Not started
P4 Progress transport | P4.2 | Backend/API | chat-progress callback → hub push | POST /api/ai-callback/chat-progress (X-Api-Key gate like AiCallbackController). Body { askId, doctorId, phase, message, occurredAt }. Handler pushes to Clients.User(doctorId) as 'ChatProgress'. | backend/src/MedicalAssistant.Api/Controllers/AiCallbackController.cs | P4.1 | AI callback fans out to the right doctor over the hub; unauthorized key rejected. | Not started
P4 Progress transport | P4.3 | Backend/Application | Backend-side phase emission | Emit 'Resolving patient' and 'Preparing context' from the ask handler around its own work (before calling AI). | backend/src/MedicalAssistant.Application/Features/Chat | P4.1,P2.2 | Backend phases appear on the hub in order before the AI's phases. | Not started
P4 Progress transport | P4.4 | AI service | AI emits phases during answer | Extend chat/answer request with askId + doctorId. Fire progress callbacks at Refining/Searching/Reviewing/Composing/Verifying boundaries. Wrap sends in try/catch and swallow (progress is convenience, never blocks the answer). | AI/src/MedicalAssistance.Ingestion.Api/Chat/GroundedAnswerService.cs + Retrieval steps | P4.2 | Each real phase produces one callback stamped with askId; a callback failure never fails the answer. | Not started
P4 Progress transport | P4.5 | Shared | Phase vocabulary constants | Define the ordered phase names once per service (backend + AI) to avoid string drift. See 'Progress Phases' sheet. | backend/src/MedicalAssistant.Application + AI/src/MedicalAssistance.Ingestion.Api/Chat | — | Both services reference the same phase identifiers. | Not started
P5 Frontend | P5.1 | Frontend | SignalR client + connection lifecycle | Add @microsoft/signalr. Build HubConnection to /hubs/chat with accessTokenFactory(JWT) + automatic reconnect. Connect on entering chat view; dispose on leave. | frontend/src/features/chat/hooks (useChatProgress.ts) | P4.1 | Browser holds one hub connection per chat view; reconnects transparently. | Not started
P5 Frontend | P5.2 | Frontend | Ephemeral progress status line | Render the latest ChatProgress.message as a status line while awaiting the answer; clear on HTTP 200. Match phase by askId; ignore stragglers. | frontend/src/features/chat/components | P5.1 | Doctor sees live 'Searching patient history…' etc.; line disappears when the answer lands. | Not started
P5 Frontend | P5.3 | Frontend | Structured citation types + [E#] parsing | Replace citations?: string[] with structured ChatCitation[]. Parse [E#] markers in answer prose into inline anchor elements bound to their citation. | frontend/src/features/chat/components/ChatMessageItem.tsx, shared/types/api | P1.1 | Every [E#] in the answer becomes a clickable anchor mapped to its citation object. | Not started
P5 Frontend | P5.4 | Frontend | Hover-quote popover + click-expand card | Hover an [E#] anchor → popover with the verbatim quote. Click → expand/scroll to a citation card (quote, document type, clinical date, session, score) in a side panel. | frontend/src/features/chat/components (CitationAnchor, CitationCard) | P5.3 | Hover shows quote; click reveals full card; keyboard-accessible. | Not started
P5 Frontend | P5.5 | Frontend | Conversation history UI | History list ('my conversations about this patient'), open a past conversation (rehydrate messages+citations), 'New conversation' button, rename, delete. | frontend/src/features/chat/pages/ChatPage.tsx, api/chatApi.ts | P2.4 | Doctor can browse, open, start, rename and delete conversations; reopened threads render citations. | Not started
P5 Frontend | P5.6 | Frontend | Failed turn + Retry | Render a Failed assistant turn with its reason and an inline Retry button calling the retry endpoint (reuses askId). | frontend/src/features/chat/components | P2.5 | Failed turn shows reason + Retry; retry resolves in place. | Not started
P5 Frontend | P5.7 | Frontend | askId generation + send path | Generate a client askId per question; POST /api/chat/ask { patientId, conversationId?, question, askId }; render the returned assistant message. | frontend/src/features/chat/hooks/useChat.ts, api/chatApi.ts | P2.2 | First and Nth questions use one send path; askId round-trips for correlation/retry. | Not started
P6 Tests & hardening | P6.1 | Backend tests | Unit tests | Window-aligned summary trigger (skip<6, every 6); auto-title; citation mapping (P1.2); askId idempotency; state machine transitions. | backend/src/MedicalAssistant test projects | P2.x,P3.x | All unit tests green; boundary cases covered. | Not started
P6 Tests & hardening | P6.2 | Backend integration | End-to-end ask (Docker/Testcontainers) | Ask over the real stack (pgvector): persist user+assistant+citations; progress callback→hub; retry idempotency. Requires Docker Desktop. | tests/ | P2.x,P4.x | Green integration run; a failed-then-retried turn ends Completed. | Not started
P6 Tests & hardening | P6.3 | AI tests | Summarize + progress emission | Test /chat/summarize contract and that each retrieval phase emits exactly one callback with the askId. | AI/src/MedicalAssistance.Ingestion.Api tests | P3.1,P4.4 | Summarize deterministic contract holds; one callback per phase. | Not started
P6 Tests & hardening | P6.4 | Docs | ADR + HOW-TO-RUN updates | ADR for backend-owned conversation state + chat progress transport; note new hub/env in HOW-TO-RUN and compose.env. | AI/docs/adr, HOW-TO-RUN.md | P4.x | Design recorded; run docs mention /hubs/chat and the callback key. | Not started
Status rollup
Not started
In progress
Done
Blocked
Total tasks

## Data Model
Data Model — backend MedicalAssistantDb (new tables)
Three tables. Cascade delete Conversation → ChatMessages → MessageCitations.
Table | Column | Type | Null | Notes
Conversations | Id | int (PK) | No | Identity.
Conversations | DoctorId | string | No | Owning doctor (matches existing doctorId string).
Conversations | PatientId | int (FK) | No | The patient this conversation is about; retrieval boundary.
Conversations | ConsultationId | int (FK) | Yes | Optional tag linking to a specific visit.
Conversations | Title | string | No | Auto from first question; renamable.
Conversations | RollingSummary | text | Yes | Null until >6 messages; phrasing/refinement input only.
Conversations | SummarizedThroughSeq | int | Yes | Sequence up to which the summary covers (window boundary).
Conversations | Status | enum int | No | Active ¦ Archived (soft delete).
Conversations | CreatedAtUtc / UpdatedAtUtc | datetimeoffset | No | Timestamps.
ChatMessages | Id | int (PK) | No | Identity.
ChatMessages | ConversationId | int (FK) | No | Parent conversation; index (ConversationId, Sequence) unique.
ChatMessages | Sequence | int | No | Order within the conversation.
ChatMessages | Role | enum int | No | User ¦ Assistant.
ChatMessages | Content | text | No | Question, or answer prose containing inline [E#] markers.
ChatMessages | State | enum int | No | Pending ¦ Completed ¦ Refused ¦ Failed (assistant turns).
ChatMessages | FailureReason | string | Yes | Set only on Failed.
ChatMessages | Language | string | Yes | Answer language (assistant turns).
ChatMessages | AskId | Guid | No | Correlation + idempotency key for the turn; indexed.
ChatMessages | CreatedAtUtc | datetimeoffset | No | Timestamp.
MessageCitations | Id | int (PK) | No | Identity.
MessageCitations | ChatMessageId | int (FK) | No | The assistant message this citation supports.
MessageCitations | Label | string | No | E1, E2, … — what the answer cites this evidence by.
MessageCitations | ChunkId | Guid | No | Source chunk.
MessageCitations | DocumentId | string | No | Source document.
MessageCitations | DocumentType | string | No | e.g. transcript, note.
MessageCitations | SessionId | string | Yes | Session link for session-scoped documents.
MessageCitations | DocumentDate | datetimeoffset | Yes | Clinical date of the source document.
MessageCitations | SourceRef | text (JSON) | Yes | Type-specific provenance (e.g. transcript line range).
MessageCitations | Quote | string (≤500) | No | Bounded verbatim quote — the reliable citation anchor.
MessageCitations | Score | double | No | Cosine similarity to the question.

## API Surface
API Surface — backend, AI service, realtime
New/changed endpoints and the SignalR hub.
Service | Method & route | Purpose | Request → Response | Auth
Backend | POST /api/chat/ask | Ask a turn (unified; auto-creates conversation) | { patientId, conversationId?, question, askId } → assistant message { conversationId, content, state, citations[] } | JWT (doctor)
Backend | POST /api/conversations | Explicit 'New conversation' | { patientId, consultationId? } → { id, title } | JWT
Backend | GET /api/patients/{patientId}/conversations | History list for a patient | → [ { id, title, updatedAt } ] | JWT
Backend | GET /api/conversations/{id}/messages | Rehydrate a conversation | → messages[] with structured citations | JWT
Backend | PATCH /api/conversations/{id} | Rename | { title } → 200 | JWT
Backend | DELETE /api/conversations/{id} | Soft delete (archive) | → 204 | JWT
Backend | POST /api/conversations/{id}/messages/{messageId}/retry | Retry a Failed turn | → assistant message (idempotent on askId) | JWT
Backend | POST /api/ai-callback/chat-progress | Receive AI phase events, fan out to hub | { askId, doctorId, phase, message, occurredAt } → 200 | X-Api-Key
Realtime | SignalR /hubs/chat (method 'ChatProgress') | Push progress to the browser | server→client { askId, phase, message, occurredAt }, routed by doctorId | JWT (accessTokenFactory)
AI service | POST /patients/{patientId}/chat/answer (extended) | Grounded answer + emit phases | + askId, doctorId in request; answer returns WHOLE (not streamed) | X-Api-Key / secret
AI service | POST /patients/{patientId}/chat/summarize (new) | Roll up older history | { priorSummary, newTurns } → { updatedSummary } | X-Api-Key / secret

## Progress Phases
Progress Phases — the ordered 'what the system is doing' vocabulary
Real phase transitions. The answer is delivered WHOLE via HTTP 200; the hub carries status only.
# | Phase (identifier) | Emitted by | Example message to the doctor
1 | ResolvingPatient | Backend | Resolving patient…
2 | PreparingContext | Backend | Preparing context…
3 | RefiningQuestion | AI service | Refining the question…
4 | SearchingHistory | AI service | Searching patient history…
5 | ReviewingEvidence | AI service | Reviewing the evidence…
6 | ComposingAnswer | AI service | Composing the answer…
7 | VerifyingCitations | AI service | Verifying citations…
✓ | (answer) | Backend HTTP 200 | Answer + citations delivered whole; frontend clears the status line.